## Defects
Bug list
Defect ID | Module | Description | Type | Severity | Priority | Status | Created Date
1 | Product Type Management | Cannot delete product type Expected result: when a user clicks on the trash icon of a product type, that product type must be deleted | Feature missing | Medium | Medium | Open | 2024-11-18
2 | Product Management | Error in order of appearance Expected result: When the user clicks on the add new product button, it must display the product adding interface first. If the product information is incorrect or missing, a message will be displayed. Please enter correct and complete information instead of displaying Display this message before displaying the interface for adding new products | Coding Logic | Medium | Low | Open | 2024-11-18
3 | Provider Management | Error adding provider Expected result: When a user adds a provider, even though the provider code is missing, the system still allows a new provider to be created | Feature missing | Serious | High | Open | 2024-11-18
4 | Provider Management | Error deleting provider When the user selects the suppliers and clicks on the trash icon at the top, a message appears: Do you want to delete the selected suppliers? If you choose yes, you will get an error. Not only will the system not delete the suppliers, but also displays the message that 0 product types have been deleted | Feature missing | Medium | Medium | Open | 2024-11-18
5 | Sell Order Management | Sell order detail error Expected result: when the user clicks on the sell order details, the total amount does not match the total amount of the products in the order | Coding Logic | Serious | High | Open | 2024-11-18
6 | Purchase Order Management | Purchase order detail error Expected result: when the user clicks on the purchase order details, the total amount does not match the total amount of the products in the order | Coding Logic | Serious | High | Open | 2024-11-18
7 | Purchase Order Management | Cannot use search function Expected result: when the user enters the purchase order code, the desired order will be displayed, but here nothing is displayed. | Feature missing | Cosmetic | Low | Open
8 | Sell Order Management | Cannot use search function Expected result: when the user enters the sell order code, the desired order will be displayed, but here nothing is displayed. | Feature missing | Cosmetic | Low | Open | 2024-11-18
9 | Provider Management | Cannot use search function Expected result: when the user enters the provider code, the desired provider will be displayed, but here nothing is displayed. | Feature missing | Cosmetic | Low | Open | 2024-11-19
10 | Product Type Management | Error when exiting product type search Expected result: when the user has looked up the product code, when user presses the exit button, user cannot exit the product search page | Feature missing | Cosmetic | Low | Open | 2024-11-19