## 17-239
Task Name | Estimate time( hour) | Take by | Actual Time | Status | Date Doing | Complete Process | Note
Requirement analyze | 16 | All | 10 | Done |  | 16
[Report 1] Project Information | 2 | Nguyen Thi Thuy Hang | 2 | Done |  | 2
[Report 1] Introduction | 2 | Tran Dinh Phuong Linh | 2 | Done |  | 2
[Report 1] Current Situation | 2 | Nguyen Khanh Huy | 2 | Done |  | 2
[Report 1] Problem Definition | 2 | Dang Thi Ngoc Minh | 2 | Done |  | 2
Draw ERD diagram | 8 | Dang Thi Ngoc Minh | 9 | Done |  | 8
Deploy database (empty database) | 4 | Tran Dinh Phuong Linh | 5 | Done |  | 4
Total | 36 |  | 88.89% |  | Done task: | 100%
[UI Mockup Desktop] Login/Register Screen | 3 | Nguyen Thi Thuy Hang | 3 | Done |  | 3
[UI Mockup Desktop] Home (Item Listing) Screen | 4 | Nguyen Thi Thuy Hang | 4 | Done |  | 4
[UI Mockup Desktop] Account Screen | 3 | Nguyen Thi Thuy Hang | 2 | Done |  | 3
[UI Mockup Desktop] Customer Screen | 4 | Tran Dinh Phuong Linh | 4 | Done |  | 4
[UI Mockup Desktop] Staff Screen | 5 | Tran Dinh Phuong Linh | 4 | Done |  | 5
[UI Mockup Desktop] Unit Screen | 5 | Nguyen Khanh Huy | 5 | Done |  | 5
[UI Mockup Desktop] Product Screen | 5 | Tran Dinh Phuong Linh | 5 | Done |  | 5
[UI Mockup Desktop] Product Style Screen | 5 | Tran Dinh Phuong Linh | 4 | Done |  | 5
[UI Mockup Desktop] Supplier screen | 5 | Nguyen Khanh Huy | 5 | Done |  | 5
[UI Mockup Desktop] Service Style Screen | 5 | Nguyen Khanh Huy | 1 | Done |  | 5
[UI Mockup Desktop] Sale Screen | 5 | Nguyen Khanh Huy | 5 | Done |  | 3
[UI Mockup Desktop] Sale Detail Screen | 4 | Dang Thi Ngoc Minh | 4 | Done |  | 2
[UI Mockup Desktop] Purchase Screen | 3 | Dang Thi Ngoc Minh | 3 | Done |  | 2
[UI Mockup Desktop] Purchase Detail Screen | 4 | Dang Thi Ngoc Minh | 5 | Done |  | 2
[UI Mockup Desktop] Service Detail List Screen | 5 | Dang Thi Ngoc Minh | 5 | Done |  | 5
[UI Mockup Desktop] Report screen | 4 | Dang Thi Ngoc Minh | 4 | Done |  | 4
Total | 69 |  | 91.3% |  | Done task: | 89.86%
[Implement UI] Login/Register Screen | 2 | Nguyen Thi Thuy Hang | 2 | Done |  | 2
[Implement UI] Home (Item Listing) Screen | 3 | Nguyen Thi Thuy Hang | 4 | Done |  | 3
[Implement UI] Account Screen | 4 | Nguyen Thi Thuy Hang | 4 | Done |  | 4
[Implement UI] Customer Screen | 2 | Tran Dinh Phuong Linh | 1 | Done |  | 2
[Implement UI] Staff Screen | 4 | Tran Dinh Phuong Linh | 4 | Done |  | 4
[Implement UI] Unit Screen | 3 | Nguyen Khanh Huy | 3 | Done |  | 3
[Implement UI] ProductScreen | 2 | Tran Dinh Phuong Linh | 2 | Done |  | 2
[Implement UI] Product Style Screen | 2 | Tran Dinh Phuong Linh | 2 | Done |  | 2
[Implement UI] Supplier Screen | 2 | Nguyen Khanh Huy | 2 | Done |  | 2
[Implement UI] Service Style Screen | 4 | Nguyen Khanh Huy | 4 | Done |  | 4
[Implement UI] Sale Screen | 2 | Nguyen Khanh Huy | 5 | Done |  | 2
[Implement UI] Sale Detail Screen | 4 | Dang Thi Ngoc Minh | 4 | Done |  | 4
[Implement UI] Purchase Screen | 2 | Dang Thi Ngoc Minh | 2 | Done |  | 2
[Implement UI] Purchase Detail Screen | 4 | Dang Thi Ngoc Minh | 4 | Done |  | 4
[Implement UI] Service Detail List Screen | 2 | Dang Thi Ngoc Minh | 2 | Done |  | 2
[Implement UI] Report Screen | 3 | Dang Thi Ngoc Minh | 3 | Done |  | 3
Total | 45 |  | 106.7% |  | Done task: | 100%